DEVELOPMENT PLAN

# AI Interview Monitoring and Detection System

Document 7 — Development Plan

Version 1.0  |  Derived from PRD v1.0 + UI/UX Specification v1.0

Development objective Convert the approved product requirements and UI/UX baseline into an ordered, testable implementation plan for a six-member team, while keeping the initial product modular, feasible and ready for later scale.

| Document Field | Value |
| --- | --- |
| Product | AI Interview Monitoring and Detection System |
| Document | Document 7 — Development Plan |
| Upstream baselines | PRD v1.0; UI/UX Specification v1.0 |
| Development model | Incremental, milestone-based implementation |
| Primary platform | Responsive web application |
| Frontend direction | React + Vite + Tailwind CSS |
| Application backend | Node.js + Express.js |
| AI service | Python + FastAPI |
| Database | MongoDB |
| Real-time direction | WebRTC + Socket.io |
| Team size | 6 members |
| Schedule basis | Relative implementation weeks; exact calendar dates TBD |

# 1. Purpose and Development Principles

This document converts the product and interface definitions into an implementation sequence. It identifies modules, work packages, dependencies, team ownership, milestones, deliverables, quality gates and handoffs.

Source-of-truth rule Development work must trace to an approved requirement or documented technical decision. The team should not add major features because they appear attractive or technically interesting unless they are explicitly approved and recorded.

Build the smallest complete interview workflow before adding advanced AI analysis.

Implement interfaces and backend contracts incrementally so frontend and backend can work in parallel.

Keep AI/monitoring modules replaceable and testable.

Prefer a modular application over premature microservices.

Treat AI findings as evidence/risk signals, not definitive proof of cheating.

Measure model and system performance instead of inventing results.

Complete a working vertical slice before optimizing individual components.

# 2. Upstream Document Traceability

| Upstream Document | Development Use |
| --- | --- |
| PRD v1.0 | Defines product scope, MVP, requirements, roles, risks, technology direction and success criteria. |
| UI/UX Specification v1.0 | Defines screen IDs, user journeys, frontend modules, component system and UI/backend capability mapping. |
| SRS — next technical baseline | Will define precise software behaviour, interfaces, acceptance criteria and technical constraints. |
| Architecture Specification — subsequent | Will define component boundaries and detailed service/data flow. |
| Database Specification — subsequent | Will define collections, fields, indexes and persistence contracts. |
| AI/ML Specification — subsequent | Will define model selection, datasets, inference and evaluation. |

Dependency note This Development Plan uses the already-approved PRD and UI/UX baselines. Exact API routes, database schemas and model names are intentionally not invented here; they must follow the later dedicated specifications.

# 3. Development Scope

## 3.1 Initial Implementation Scope

| Module | Scope | Priority |
| --- | --- | --- |
| M01 | Project foundation and development environment | P0 |
| M02 | Authentication and role-aware access | P0 |
| M03 | Public website | P1 |
| M04 | Interview management | P0 |
| M05 | Interviewee system check | P0 |
| M06 | Interview room / WebRTC workflow | P0 |
| M07 | Video monitoring and CV event detection | P0 |
| M08 | Real-time event and alert pipeline | P0 |
| M09 | Evidence/event persistence | P0 |
| M10 | Integrity view and basic report | P1 |
| M11 | Cross-module testing and evaluation | P0 |
| M12 | Packaging, demo deployment and documentation | P1 |

## 3.2 Deferred Development Scope

Advanced audio/voice analysis.

Advanced NLP-based AI-assistance analysis.

Deepfake detection.

Advanced identity verification.

ATS integrations.

Enterprise multi-tenant infrastructure.

Subscription/payment system.

Mobile application.

Full ATS, HRMS or coding-assessment platform.

# 4. Development Architecture Baseline

The implementation follows the technology direction already recorded in the PRD.

| Layer | Baseline | Development Implication |
| --- | --- | --- |
| Frontend | React + Vite + Tailwind CSS | Build reusable role-specific modules and shared components. |
| Application Backend | Node.js + Express.js | Implement authentication, interview/session APIs and application orchestration. |
| AI Service | Python + FastAPI | Expose modular monitoring/analysis capabilities to the application. |
| Database | MongoDB | Persist users, interviews, events, alerts, evidence references and reports as defined later. |
| CV | OpenCV + MediaPipe | Implement selected observable video signals. |
| NLP | Transformers/BERT-family tooling where justified | Future/proposed; do not block MVP unless explicitly approved. |
| Audio | Local speech-to-text + Librosa where useful | Future/proposed; exact model TBD. |
| Real-time | WebRTC + Socket.io | Support interview media and live event/alert communication. |
| Containerization | Docker | Provide reproducible development/runtime environment. |

# 5. Module Breakdown

| ID | Module | Responsibility | Depends On |
| --- | --- | --- | --- |
| M01 | Foundation | Repository, environment, shared configuration, coding conventions, base frontend/backend/AI services. | All modules |
| M02 | Authentication & Authorization | Sign-in, session handling, role-aware routing and backend authorization. | M03–M12 |
| M03 | Public Website | Landing, Product, Features, How It Works and navigation CTAs. | M02 |
| M04 | Interview Management | Create, retrieve, update and manage interview sessions/invitations. | M02, M05, M06 |
| M05 | Interviewee System Check | Camera, microphone, connectivity and relevant browser capability checks. | M02, M06 |
| M06 | Interview Room | Interview session UI, media controls, session lifecycle and connection states. | M04, M05, real-time layer |
| M07 | Video Monitoring / CV | Webcam signal capture/processing and selected suspicious-event detectors. | M06, AI service |
| M08 | Real-Time Events & Alerts | Event transport, alert generation/presentation and event lifecycle. | M07, database |
| M09 | Evidence & Persistence | Store/retrieve event metadata and evidence references. | M04, M07, M08, database |
| M10 | Integrity View & Reports | Risk/evidence presentation and post-interview report. | M08, M09 |
| M11 | Testing & Evaluation | Unit, integration, E2E, UI, CV and performance validation. | All modules |
| M12 | Release & Documentation | Build, configuration, deployment packaging, demo preparation and technical documentation. | M11 |

# 6. Detailed Work Packages and Tasks

| Task | Module | Work Package | Description | Priority | Owner | Dependency |
| --- | --- | --- | --- | --- | --- | --- |
| DEV-001 | M01 | Create repository structure | Create frontend, backend, AI-service and documentation areas. | P0 | Team Lead + Backend | None |
| DEV-002 | M01 | Local environment | Define environment variables, local database/service startup and developer setup instructions. | P0 | Backend + DevOps/QA | DEV-001 |
| DEV-003 | M01 | Shared UI foundation | Set up Tailwind, routing, layout, typography and reusable base components. | P0 | Frontend | DEV-001 |
| DEV-004 | M01 | Code quality baseline | Linting, formatting, error handling conventions and basic Git workflow. | P1 | Team Lead | DEV-001 |
| DEV-005 | M02 | Authentication UI | Implement Sign In and authentication states. | P0 | Frontend | DEV-003 |
| DEV-006 | M02 | Authentication backend | Implement credential/session handling according to SRS security requirements. | P0 | Backend | DEV-002 |
| DEV-007 | M02 | Role-aware routing | Route HR, Interviewer and Interviewee to permitted experiences. | P0 | Frontend + Backend | DEV-005, DEV-006 |
| DEV-008 | M03 | Public website | Build landing, product, features and how-it-works sections. | P1 | Frontend | DEV-003 |
| DEV-009 | M04 | Interview API | Implement interview session creation/retrieval/update lifecycle. | P0 | Backend | DEV-006 |
| DEV-010 | M04 | HR interview screens | Create Interview and Interview Management interfaces. | P0 | Frontend | DEV-007, DEV-009 |
| DEV-011 | M04 | Interviewer dashboard | Assigned/upcoming/ongoing/completed interview views. | P1 | Frontend | DEV-007, DEV-009 |
| DEV-012 | M05 | System-check UI | Camera/microphone/network/browser readiness interface and states. | P0 | Frontend | DEV-007 |
| DEV-013 | M05 | System-check logic | Implement supported client-side readiness checks. | P0 | Frontend + Backend | DEV-012 |
| DEV-014 | M06 | Interview room UI | Video layout, controls, connection state, monitoring notice and error states. | P0 | Frontend | DEV-012 |
| DEV-015 | M06 | Media session | Implement WebRTC/signalling integration according to architecture specification. | P0 | Backend + Frontend | DEV-014 |
| DEV-016 | M07 | CV service foundation | Create FastAPI AI-service structure and monitoring interfaces. | P0 | AI/CV | DEV-002 |
| DEV-017 | M07 | Video signal capture | Connect supported video frames/signals to CV processing pipeline. | P0 | AI/CV + Frontend | DEV-015, DEV-016 |
| DEV-018 | M07 | Initial CV detectors | Implement only validated MVP observable events selected in SRS/AI specification. | P0 | AI/CV | DEV-017 |
| DEV-019 | M08 | Event schema/contract | Define event payload contract based on SRS/database specification. | P0 | Backend + AI | DEV-018 |
| DEV-020 | M08 | Real-time event transport | Stream supported events to authorized monitoring clients. | P0 | Backend | DEV-019 |
| DEV-021 | M08 | Alert UI | Implement live alert cards/toasts, event timeline and severity/confidence display. | P0 | Frontend | DEV-020 |
| DEV-022 | M09 | Event persistence | Persist timestamped events and evidence references. | P0 | Backend + Database | DEV-019 |
| DEV-023 | M09 | Evidence review UI | Open event details and available evidence/context. | P1 | Frontend | DEV-022 |
| DEV-024 | M10 | Integrity view | Display risk indicators only if approved and supported by AI specification. | P1 | Frontend + AI | DEV-022 |
| DEV-025 | M10 | Report generation | Build post-interview event summary/report interface. | P1 | Backend + Frontend | DEV-022, DEV-024 |
| DEV-026 | M11 | Unit tests | Test frontend components, backend services and AI modules. | P0 | All members | Relevant module complete |
| DEV-027 | M11 | Integration tests | Validate browser → backend → AI → event → alert → persistence flow. | P0 | QA + Backend + AI | M02–M10 |
| DEV-028 | M11 | E2E interview test | Run complete recruiter/interviewer/interviewee workflow. | P0 | QA + Frontend | M02–M10 |
| DEV-029 | M11 | CV evaluation | Evaluate selected scenarios using defined dataset/test protocol. | P0 | AI/CV | M07 |
| DEV-030 | M11 | Performance test | Measure real-time latency/resource use and document results. | P0 | Backend + AI + QA | M08–M10 |
| DEV-031 | M12 | Release build | Build reproducible release candidate and configuration documentation. | P1 | Team Lead + DevOps/QA | M11 |
| DEV-032 | M12 | Demo preparation | Prepare controlled demonstration dataset/scenarios and final walkthrough. | P1 | All members | DEV-031 |

# 7. Team Allocation

The following allocation converts the previously discussed six-member team structure into development ownership. It is a proposed working allocation and can be adjusted by the team without changing product scope.

| Member | Primary Responsibility | Secondary Responsibility | Key Modules |
| --- | --- | --- | --- |
| Asifur Rahman — 1AT24CD017 | Product / Technical Lead | Integration, architecture coordination, release | M01, M02, M04, M11, M12 |
| Aakash Raj — 1AT24CS001 | Frontend Engineer | UI component system and responsive design | M03, M05, M06, M10 |
| Aarav Singh — 1AT24CS002 | Backend Engineer | API, session and persistence integration | M02, M04, M08, M09 |
| Ayush — 1AT24CS032 | Computer Vision Engineer | CV evaluation and optimization | M07 |
| Ashwani Kumar Mishra — 1AT24CD030 | NLP / Audio Engineer | Future audio/NLP groundwork; integration support | M07 support; future M13 |
| Mohit Kumar — 1AT24CD122 | QA / AI-Fusion Engineer | Testing, evaluation, event/risk integration | M08, M10, M11 |

Scope note Advanced NLP/audio work is intentionally not allowed to block the MVP. The assigned NLP/audio member can support integration, dataset/evaluation preparation and future capability design while the core webcam/event pipeline is completed.

# 8. Responsibility Matrix

| Work Area | Lead | Contributors | Approval / Review |
| --- | --- | --- | --- |
| Product scope | Asifur | All | Team + Faculty Guide as required |
| Frontend/UI | Aakash | Asifur, Mohit | Frontend review |
| Backend/API | Aarav | Asifur, Mohit | Backend review |
| Computer Vision | Ayush | Mohit, Asifur | AI/ML review |
| Audio/NLP future work | Ashwani | Ayush, Mohit | AI/ML review |
| Real-time pipeline | Aarav | Aakash, Ayush, Mohit | Integration review |
| Testing/evaluation | Mohit | All | Team review |
| Release/demo | Asifur | All | Team + Faculty Guide |

# 9. Dependency Graph and Implementation Order

The recommended order is dependency-driven rather than feature-count-driven.

| Stage | Must Be Working Before | Reason |
| --- | --- | --- |
| 1. Foundation | Any feature work | Shared repository, environment and conventions. |
| 2. Auth + roles | Role-specific dashboards | Authorization is a prerequisite for protected workflows. |
| 3. Interview management | Interview room | A live room needs a valid interview/session context. |
| 4. System check | Interview room entry | Candidate readiness must be established before joining. |
| 5. Interview room/media | CV monitoring | Monitoring needs a live media/session source. |
| 6. CV/event detection | Live alerts | Alerts need actual event producers. |
| 7. Event transport | Evidence/reporting | Reports need structured events. |
| 8. Persistence/evidence | Integrity/report UI | The UI needs durable event/evidence data. |
| 9. Testing | Release | Release is blocked until critical workflows are validated. |

Critical path Foundation → Authentication → Interview Management → System Check → Interview Room/WebRTC → CV Monitoring → Event Stream → Persistence → Alerts/Reports → End-to-End Validation → Release

# 10. Milestone and Sprint Plan

The schedule uses relative weeks so it remains valid regardless of the team's actual start date. Exact dates should be added only after the team confirms the academic calendar and available hours.

| Sprint / Week | Focus | Major Deliverables | Exit Gate |
| --- | --- | --- | --- |
| Week 1 | Foundation | Repo, environment, frontend shell, backend shell, AI-service shell, coding conventions | All members can run the project locally |
| Week 2 | Auth + public site | Sign-in, role routing, base dashboards, landing website | Protected role routing works |
| Week 3 | Interview management | Create/manage interview, interviewer dashboard, interview session lifecycle | Interview can be created and retrieved |
| Week 4 | Candidate readiness | System check + interview room UI + media foundation | Candidate reaches a valid interview room |
| Week 5 | Real-time interview | WebRTC/session integration + live monitoring shell | Controlled two-party/live session works |
| Week 6 | Computer vision | CV service + selected MVP event detectors | Controlled test events can be generated |
| Week 7 | Events + alerts | Socket/event stream, alert UI, event timeline, persistence | Detected event reaches authorized monitoring UI and is stored |
| Week 8 | Integrity/report | Evidence review, basic integrity view, report | End-to-end interview record can be reviewed |
| Week 9 | Testing/evaluation | Unit/integration/E2E/CV/performance testing | Critical defects addressed; measurements captured |
| Week 10 | Release/demo | Release candidate, documentation, demo scenario, final QA | Release/demo acceptance checklist passes |

# 11. Milestone Acceptance Gates

| Gate | Minimum Condition |
| --- | --- |
| G1 — Foundation Complete | Repository, local setup and base services run consistently for all developers. |
| G2 — Auth Complete | Role-aware protected routes and backend authorization work for required roles. |
| G3 — Interview Workflow Complete | HR can create an interview and Interviewer/Interviewee can access the correct workflow. |
| G4 — Live Session Complete | Interviewee can pass system check and enter the interview room; media/session behaviour is testable. |
| G5 — Monitoring Complete | Selected CV events can be produced under controlled scenarios. |
| G6 — Alerting Complete | A supported event can be transported, displayed and associated with the interview. |
| G7 — Evidence Complete | Event metadata and evidence references can be persisted and reviewed. |
| G8 — Report Complete | Post-interview report presents supported events and indicators without unsupported claims. |
| G9 — Validation Complete | Critical workflow, AI/CV and performance tests have documented results. |
| G10 — Release Complete | Known critical defects are resolved or explicitly accepted; demo and setup documentation are ready. |

# 12. Git and Repository Workflow

A simple branch strategy is recommended for a six-member student team.

| Branch / Convention | Purpose |
| --- | --- |
| main | Stable, review-approved code only. |
| develop | Integration branch if the team needs a shared pre-release branch. |
| feature/<module>-<short-name> | Individual feature work. |
| fix/<issue>-<short-name> | Bug fixes. |
| release/vX.Y | Release candidate preparation if needed. |

Each feature should reference a development task ID.

Keep commits small enough to review.

Do not commit secrets or API keys.

Open a pull request before merging substantial changes.

At least one teammate should review code touching authentication, real-time communication, data persistence or AI scoring.

Keep generated datasets/media out of Git when they are too large or sensitive; use an approved data-storage approach instead.

# 13. Proposed Repository Structure

This structure is a planning baseline, not a claim that the repository already exists.

ai-interview-monitoring/
├── frontend/
│   ├── src/
│   │   ├── components/
│   │   ├── pages/
│   │   ├── modules/
│   │   │   ├── hr/
│   │   │   ├── interviewer/
│   │   │   └── interviewee/
│   │   ├── services/
│   │   ├── hooks/
│   │   └── styles/
│   └── tests/
├── backend/
│   ├── src/
│   │   ├── routes/
│   │   ├── controllers/
│   │   ├── services/
│   │   ├── middleware/
│   │   ├── models/
│   │   └── utils/
│   └── tests/
├── ai-service/
│   ├── app/
│   │   ├── api/
│   │   ├── monitoring/
│   │   ├── cv/
│   │   ├── audio/
│   │   ├── nlp/
│   │   └── fusion/
│   └── tests/
├── docs/
├── scripts/
├── docker/
└── README.md

# 14. Module Contracts

| Contract | Producer | Consumer | Rule |
| --- | --- | --- | --- |
| Authentication/session | Backend | Frontend | Frontend receives only the information required for routing/session state. |
| Interview/session | Backend | HR/Interviewer/Interviewee UI | All actions must be authorization-checked. |
| Media session | WebRTC/signalling layer | Interview Room / Live Monitoring | Media state must be observable and recoverable. |
| Monitoring event | AI/CV service | Event pipeline | Event includes interview context, timestamp and applicable confidence/model metadata. |
| Alert | Event pipeline | Interviewer/HR UI | Alert is a presentation of a relevant event, not a definitive accusation. |
| Evidence reference | Monitoring/persistence | Alert/Report UI | Reference must resolve only for authorized users. |
| Report | Report service | HR/Interviewer | Report summarizes supported evidence and risk indicators. |

# 15. Testing Strategy

| Level | What to Test | Owner(s) | Output |
| --- | --- | --- | --- |
| Unit | Frontend components, backend services, AI utilities | Module owners | Automated unit tests |
| Integration | API ↔ DB, backend ↔ AI service, event pipeline | Backend + AI + QA | Integration test results |
| UI | Navigation, forms, states, responsive behaviour | Frontend + QA | UI test checklist |
| E2E | HR → interview → interviewee system check → room → monitoring → report | QA + All | End-to-end test report |
| CV/AI | Controlled normal/suspicious scenarios | Ayush + Mohit | Metrics and error analysis |
| Performance | Event latency, resource use, concurrency baseline | Aarav + Mohit | Benchmark report |
| Security | Auth, authorization, secret handling, evidence access | Aarav + Asifur | Security checklist |

Measurement rule No model accuracy, F1, false-positive rate, latency or concurrency figure should be placed in project documentation as an achieved result until the team has actually measured it.

# 16. Definition of Done

The task implements the approved requirement or documented technical decision.

The intended user flow works in the supported environment.

Loading, empty, error and permission states are handled where relevant.

Authorization is enforced server-side for protected data/actions.

Sensitive credentials/secrets are not committed.

Relevant unit/integration tests are present.

The feature is manually tested in the intended workflow.

UI is consistent with the UI/UX specification.

Requirement and task IDs are referenced in the implementation/PR where practical.

Known limitations are documented.

The change does not silently contradict an upstream document.

# 17. Issue Priority and Severity

| Level | Meaning | Release Treatment |
| --- | --- | --- |
| P0 | Required for core product workflow or safety/security. | Must be completed or explicitly approved before release. |
| P1 | Important product capability but not necessary for the core vertical slice. | May be deferred if it threatens the critical path. |
| P2 | Enhancement or future capability. | Do not block MVP. |
| Blocker | Prevents a core workflow from operating or creates a serious security/data issue. | Immediate attention. |
| Critical defect | Severe failure in authentication, session integrity, monitoring, data access or core workflow. | Release blocker unless explicitly accepted. |

# 18. Development Risks and Responses

| Risk | Development Response |
| --- | --- |
| CV detector performs poorly | Start with a small set of observable events; create controlled test scenarios; measure precision/recall and error cases. |
| WebRTC integration consumes time | Build and test a minimal media/session slice before advanced monitoring. |
| Real-time pipeline is slow | Use event-driven processing, sampling and measured benchmarks. |
| Frontend/backend contract mismatch | Agree on interface contracts before implementation and test integration early. |
| AI work blocks core product | Keep AI service modular and use a limited MVP detector set. |
| Team members work in isolation | Integrate at least once per sprint and maintain shared task IDs. |
| Scope creep | Require new feature approval and classify it as MVP, P1 or future. |
| Free infrastructure limitations | Prototype locally and record actual resource needs before production claims. |
| False-positive concerns | Evidence-first UX, confidence separation, human review and documented limitations. |
| Sensitive data handling | Use controlled/consented test data and minimize unnecessary retention. |

# 19. Development Environments

| Environment | Purpose | Data |
| --- | --- | --- |
| Local Development | Individual feature development. | Synthetic/controlled development data. |
| Integration / Test | Combined frontend/backend/AI testing. | Controlled test scenarios only. |
| Demo / Staging | Stable demonstration before presentation/pilot. | Approved synthetic or consented demo data. |
| Production | Future SaaS deployment. | Requires finalized security, privacy, retention and infrastructure specifications. |

Production deployment is intentionally not treated as part of the MVP until the infrastructure and security documents define the required controls.

# 20. Development Data Strategy

Use controlled, consent-based scenarios for AI/CV testing.

Include normal interview scenarios and deliberately constructed suspicious-event scenarios.

Keep labels and scenario definitions separate from model code.

Record the dataset/test-set version used for each evaluation.

Do not claim general-world performance from a small controlled dataset.

Do not use sensitive personal data unnecessarily.

The final dataset schema and evaluation protocol will be defined in the AI/ML and Testing documents.

# 21. Development Deliverables

| Deliverable ID | Deliverable | Source / Trace |
| --- | --- | --- |
| DEL-001 | Working repository and developer setup | PRD technology direction + DEV-001/002 |
| DEL-002 | Public website | UX-PUB-* |
| DEL-003 | Authentication and role-aware application | PRD-FR-001 + UX-AUTH-* |
| DEL-004 | HR interview management | PRD-FR-002 + UX-HR-* |
| DEL-005 | Interviewer dashboard and live monitoring | PRD-FR-004 to FR-009 + UX-INT-* |
| DEL-006 | Interviewee dashboard/system check/interview room | PRD-FR-003/004 + UX-CAN-* |
| DEL-007 | CV monitoring/event detection | PRD-FR-005/006 + AI specification |
| DEL-008 | Real-time alerts and event history | PRD-FR-007/008 + UX-INT-* |
| DEL-009 | Integrity view/report | PRD-FR-009/010 + UX-REP-001 |
| DEL-010 | Automated and manual test evidence | PRD success criteria + TEST-* |
| DEL-011 | Release/demo package | Development Plan + Infrastructure/Testing |

# 22. Sprint Tracking Template

| Field | Required Content |
| --- | --- |
| Sprint Goal | One sentence describing the sprint outcome. |
| Tasks | DEV-* task IDs planned for the sprint. |
| Owner | Responsible member. |
| Dependency | Blocked-by task/module, if any. |
| Status | Not Started / In Progress / Review / Done / Blocked. |
| Evidence | PR, test result, screenshot, benchmark or demo reference. |
| Known Issues | Open defects/limitations. |
| Carry-over | Tasks intentionally moved to next sprint and reason. |
| Decision Changes | Any approved deviation from the baseline documents. |

# 23. Development Plan Acceptance Criteria

All MVP modules have an identified owner.

Critical dependencies are explicitly ordered.

Each major implementation task maps to a module and upstream requirement/UI area.

The six-member team has defined primary and secondary responsibilities.

Milestones have objective exit gates.

Testing is planned alongside implementation rather than only at the end.

No unverified AI/model performance claims are embedded in the plan.

Advanced capabilities are clearly separated from MVP work.

Release is blocked by critical workflow/security failures.

The plan can be traced forward into architecture, database, AI/ML and testing documents.

# 24. Handoff to Subsequent Documents

| Document | Development Dependency |
| --- | --- |
| System Architecture | Module boundaries, event flow, WebRTC/signalling, AI-service interaction and deployment topology must refine this plan. |
| Database Specification | Persistence tasks M09 and event/report flows require the finalized schema. |
| AI/ML Specification | M07 and AI-related tasks require the selected models, datasets, inference interfaces and evaluation protocol. |
| Infrastructure Plan | M12 release/deployment work requires actual resource, storage, networking and environment requirements. |
| Testing & Evaluation Plan | M11 must inherit requirement IDs, scenarios and metrics from the finalized test specification. |
| Startup/Product Roadmap | Post-MVP modules and future productization should reflect what is actually validated and implemented. |

Final baseline rule Document 7 is an execution plan, not evidence that the planned modules already exist. Implementation status must be tracked separately. When the team completes a module, the status should be supported by code, tests or demonstrable evidence.